## High Level Milestones
Project Sponsor: |  | Section Manager: Information Technology, ICT: Man and Gen (Mr R Poliah )
Business Owner: |  | Chief Librarian, KIS: PISC: Library Administration ( Mr Albert Ntunja )
Project Manager: |  | Manager: ICT Business Support, ICT: IT Systems and Application Support Unit (Zandisile Msitshana)
Reporting Period:
Beneficiaries: |  | Public
Compiled By: |  | Ms Noeleen Turdon
| Legend |  | Green No deviation |  |  | Amber Medium deviation |  | Red High deviation
ID | Deliverable Description | [6 empty] | Legend
Go live …….
| Project Milestones and Tasks (0%) |  |  | Responsibility | Planned Date | Actual Date | Actual % completed | Variance %
1 | A. Functional specification
1.1 | Sourcing of sample documents video |  |  | Zandi | 2018-06-05 | 2018-05-30 | 100%
1.1 | Sourcing of sample documents audio |  |  | Zandi | 2018-06-05 | 2018-05-30 | 100%
1.2 | Testing related document functions |  |  | PIC team | 2018-06-05 | TBC | 0%
2 | B. D-Space E-Repository solution (0%)
2.1 | Prepare DEV environment |  |  | Vusani | 2018-06-05 | 2018-06-04 | 100%
2.2 | Set-up sever |  |  | Vusani | 2018-06-05 | 2018-06-04 | 100%
2.3 | Migrate folder structure |  |  | Vusani | 2018-06-05 | 2018-06-04 | 100%
2.4 | Publish environment |  |  | Vusani | TBC | TBC | 100%
3 | C. User acceptance testing (0%)
3.1 | PIC internal testing |  |  | PIC team | 2018-06-12 | 2017-11-02 | 100%
4 | D. Functionality assessment (0%)
4.1 | PIC internal assessment |  |  | PIC team | 2018-06-12 | 2018-06-12 | 80%
5 | E. Expansion roadmap (0%)
5.1 | Initiation phase |  |  | TBC | TBC | TBC | 100%
5.2 | Implementation phase |  |  | TBC | TBC | TBC | 0%
6 | F. Change Management (0%)
6.1 | Stakeholder Engagement with: |  |  | Mr Ntunja/ PIC team | TBC | TBC | 0%
6.1.1 | KISD management forum |  |  | Mr Ntunja | TBC | TBC | 0%
6.1.2 | Sound and Vision |  |  | PIC team | TBC | TBC | 0%
6.1.3 | PSC |  |  | PIC team | TBC | TBC | 0%
6.1.4 | NCOP Table |  |  | PIC team | TBC | TBC | 0%
6.1.5 | International Relation |  |  | PIC team | TBC | TBC | 0%
6.1.6 | Committees |  |  | PIC team | TBC | TBC | 0%
6.1.7 | NA Table |  |  | PIC team | TBC | TBC | 0%
6.1.8 | Language services |  |  | PIC team | TBC | TBC | 0%
6.1.9 | Hansard |  |  | PIC team | TBC | TBC | 0%
6.1.10 | Documentation |  |  | PIC team | TBC | TBC | 0%
7 | G. Training/ knowledge transfer
7.1 | PIC internal staff training |  |  | PIC team | TBC | TBC | 0%
7.2 | Stakeholder training |  |  | PIC team | TBC | TBC | 0%
8 | H. Closure
8.1
8.2
9 | I. Maintenance and support
9.1
9.2
10 | J. Deviation | [7 empty] | .
10.1
10.2
11 | K. Action plan for deviation
11.1
11.2
12 | L. Current risks for this reporting period:
12.1 | Server storage space
12.2 | Quality of digitised resources
12.3 | Staff capacity